## Summary
PROJECT: Event Lottery System
Project Metrics
Total User Stories | 46
Total Story Points | 185
Number of Epics | 5
High Risk Stories | 6
Medium Risk Stories | 14
Low Risk Stories | 26
Release Planning
Milestone | Stories | Points | Sprints
Halfway Checkpoint (MVP) | 27 | 114 | 4-5
Final Release | 19 | 71 | 3-4
Total | 46 | 185 | 7-9
Epics Summary
Epic | Stories | Points | Risk Level | Release
1: User Auth & Profile | 5 | 16 | Lostly Low | Halfway/Final
2: Event Browsing | 12 | 54 | Low-Medium-High | Halfway/Final
3: Notifications | 5 | 18 | Low-Medium | Mostly Halfway
4: Event Management | 16 | 73 | Low-Medium-High | Halfway/Final
5: Admin Management | 8 | 24 | Mostly Low | Final

## All Stories
Story | ID | Epic | Title | Role | Story | Points | Risk | Release | Rationale | Dependencies
1 | US 01.01.01 | 2: Event Browsing | Join waiting list for event | Entrant | I want to join the waiting list for a specific event | 5 | Medium | Halfway | Core MVP feature, must handle real-time updates, prevent duplicates | US 01.02.01, US 02.01.01
2 | US 01.01.02 | 2: Event Browsing | Leave waiting list | Entrant | I want to leave the waiting list for a specific event | 3 | Low | Halfway | Simple delete operation from waiting list | US 01.01.01
3 | US 01.01.03 | 2: Event Browsing | Browse events | Entrant | I want to be able to see a list of events that I can join the waiting list for | 3 | Low | Halfway | Core MVP feature, simple list display from Firestore | US 02.01.01
4 | US 01.01.04 | 2: Event Browsing | Filter events by interest and availability | Entrant | I want to filter events by interest and availability | 8 | High | Final | Complex search logic, database indexing needed, performance critical | US 01.01.03
5 | US 01.02.01 | 1: User Auth & Profile | Provide personal information (name, email, phone) | Entrant | I want to provide my personal information such as name, email and optional phone number in the app | 3 | Low | Halfway | Foundation for user profiles, simple form validation, low risk | None
6 | US 01.02.02 | 1: User Auth & Profile | Update profile information | Entrant | I want to update information such as name, email and contact information on my profile | 2 | Low | Halfway | Basic CRUD operation, similar to create profile | US 01.02.01
7 | US 01.02.03 | 2: Event Browsing | View event registration history | Entrant | I want to have a history of events I have registered for, whether I was selected or not | 5 | Medium | Final | Nice-to-have feature for user, requires data aggregation | US 01.01.01
8 | US 01.02.04 | 1: User Auth & Profile | Delete profile | Entrant | I want to delete my profile if I no longer wish to use the app | 3 | Low | Final | Data deletion important (GDPR), cascade deletes needed | US 01.02.01
9 | US 01.04.01 | 3: Notifications | Notification when chosen (won lottery) | Entrant | I want to receive notification when I am chosen to participate from the waiting list | 5 | Medium | Halfway | Core MVP feature, requires notification service integration | US 02.05.02
10 | US 01.04.02 | 3: Notifications | Notification when not chosen (lost lottery) | Entrant | I want to receive notification when I am not chosen on the app | 3 | Low | Halfway | Similar to selection but simpler content | US 02.05.02
11 | US 01.04.03 | 1: User Auth & Profile | Opt out of notifications | Entrant | I want to opt out of notifications | 3 | Low | Final | Simple toggle setting in preferences | US 01.02.01
12 | US 01.05.01 | 2: Event Browsing | Another chance if selected user declines | Entrant | I want another chance to be chosen from the waiting list if a selected user declines | 5 | Medium | Halfway | Core lottery feature, replacement draws, depends on lottery and notification systems | US 01.01.01, US 02.05.02
13 | US 01.05.02 | 2: Event Browsing | Accept invitation to participate | Entrant | I want to be able to accept the invitation to register/sign up when chosen to participate in an event | 5 | Medium | Halfway | Core acceptance flow, state management, notifications | US 02.05.02
14 | US 01.05.03 | 2: Event Browsing | Decline invitation to participate | Entrant | I want to be able to decline an invitation when chosen to participate in an event | 3 | Low | Halfway | Simple state change, triggers replacement draw | US 02.05.02
15 | US 01.05.04 | 2: Event Browsing | See total entrants on waiting list | Entrant | I want to know how many total entrants are on the waiting list for an event | 2 | Low | Halfway | Simple count aggregation, useful for user to know odds | US 01.01.03
16 | US 01.05.05 | 2: Event Browsing | Understand lottery selection criteria | Entrant | I want to be informed about the criteria or guidelines for the lottery selection process | 2 | Low | Final | Educational/transparency feature, simple informational content | US 02.05.02
17 | US 01.06.01 | 2: Event Browsing | View event details via QR code | Entrant | I want to view event details via QR code | 8 | High | Halfway | Camera integration, platform-specific, QR library needed | US 02.01.01
18 | US 01.06.02 | 2: Event Browsing | Sign up for event by QR code | Entrant | I want to be able to sign up for an event by scanning QR code | 5 | Medium | Halfway | Combines QR scanning with join waiting list | US 01.06.01, US 01.01.01
19 | US 01.07.01 | 1: User Auth & Profile | Device-based authentication (no password) | Entrant | I want device identification without password | 5 | High | Halfway | Custom approach, security critical, cryptographic device ID needed | US 01.02.01
20 | US 02.01.01 | 4: Event Management | Create event with QR code | Organizer | I want to create a new event and generate a unique promotional QR code | 8 | High | Halfway | Multiple complex components, QR generation, image handling, 8 pts justified | US 01.02.01
21 | US 02.01.04 | 4: Event Management | Set registration period | Organizer | I want to set registration period | 3 | Low | Halfway | Part of event creation form, simple validation logic | US 02.01.01
22 | US 02.02.01 | 4: Event Management | View waiting list | Organizer | I want to view the list of entrants who joined my event waiting list | 5 | Medium | Halfway | Important monitoring tool, fetch and display real-time data | US 01.01.01, US 02.01.01
23 | US 02.02.02 | 4: Event Management | View map of entrants | Organizer | I want to see on a map where entrants joined my event waiting list from | 8 | High | Final | Google Maps API integration, privacy concerns, not MVP | US 01.02.01, US 02.02.03
24 | US 02.02.03 | 4: Event Management | Enable/disable geolocation | Organizer | I want to enable or disable the geolocation requirement for my event | 5 | Medium | Final | Companion to map feature, privacy control | US 02.01.01
25 | US 02.03.01 | 4: Event Management | Limit waiting list size (optional) | Organizer | I want to OPTIONALLY limit the number of entrants who can join my waiting list | 3 | Low | Final | Optional feature for organizer control | US 02.01.01
26 | US 02.04.01 | 4: Event Management | Upload event poster | Organizer | I want to upload an event poster to the event details page | 5 | Medium | Halfway | Visual appeal, image upload handling, Firebase Storage integration | US 02.01.01
27 | US 02.04.02 | 4: Event Management | Update event poster | Organizer | I want to update an event poster | 3 | Low | Halfway | Extension of upload, simple replace operation | US 02.04.01
28 | US 02.05.01 | 4: Event Management | Organizer triggers lottery draw | Organizer | I want to draw lottery (organizer initiates draw after registration closes) | 3 | Medium | Halfway | UI trigger for lottery system, workflow integration | US 02.05.02
29 | US 02.05.02 | 4: Event Management | Lottery algorithm (random sampling) | System | I want to set the system to sample a specified number of attendees | 8 | High | Halfway | Core system integrity, fairness critical, rigorous testing needed | US 01.01.01
30 | US 02.05.03 | 4: Event Management | Draw replacement applicant | Organizer | I want to draw a replacement applicant when selected applicant cancels | 5 | Medium | Halfway | Core feature for managing declines, uses lottery algorithm | US 02.05.02, US 01.04.01
31 | US 02.06.01 | 4: Event Management | View selected/invited entrants | Organizer | I want to view a list of all chosen entrants who are invited to apply | 3 | Low | Halfway | Important status monitoring, similar to waiting list view | US 02.05.02
32 | US 02.06.02 | 4: Event Management | View cancelled entrants | Organizer | I want to see a list of all the cancelled entrants | 3 | Low | Final | Tracking feature for management
33 | US 02.06.03 | 4: Event Management | View final enrolled list | Organizer | I want to see a final list of entrants who enrolled for the event | 3 | Low | Halfway | Essential for attendance tracking | US 01.05.02
34 | US 02.06.04 | 4: Event Management | Cancel entrant (organizer action) | Organizer | I want to cancel entrants that did not sign up for the event | 3 | Low | Halfway | Management/enforcement tool, simple status change | US 02.06.03
35 | US 02.06.05 | 4: Event Management | Export enrolled list (CSV) | Organizer | I want to export a final list of entrants in CSV format | 5 | Medium | Final | Data export for external use, CSV generation | US 02.06.03
36 | US 02.07.01 | 3: Notifications | Send notifications to waiting list | Organizer | I want to send notifications to all entrants on the waiting list | 5 | Medium | Halfway | Organizer communication tool, bulk notification delivery | US 01.01.01
37 | US 02.07.02 | 3: Notifications | Send notifications to selected entrants | Organizer | I want to send notifications to all selected entrants | 3 | Low | Halfway | Same as above but for selected only, narrower recipient pool | US 02.05.02
38 | US 02.07.03 | 3: Notifications | Send notifications to cancelled entrants | Organizer | I want to send a notification to all cancelled entrants | 2 | Low | Final | Optional communication, very limited recipient pool | US 02.05.03
39 | US 03.01.01 | 5: Admin Management | Remove events | Admin | I want to remove events | 3 | Low | Final | Admin moderation capability
40 | US 03.02.01 | 5: Admin Management | Remove profiles | Admin | I want to remove profiles | 3 | Low | Final | Admin moderation capability
41 | US 03.03.01 | 5: Admin Management | Remove images | Admin | I want to remove images | 2 | Low | Final | Admin moderation capability
42 | US 03.04.01 | 5: Admin Management | Browse events (admin view) | Admin | I want to browse events | 3 | Low | Final | Admin visibility into system
43 | US 03.05.01 | 5: Admin Management | Browse profiles (admin view) | Admin | I want to browse profiles | 3 | Low | Final | Admin visibility into system
44 | US 03.06.01 | 5: Admin Management | Browse images (admin view) | Admin | I want to be able to browse images that are uploaded | 2 | Low | Final | Admin visibility and moderation
45 | US 03.07.01 | 5: Admin Management | Remove policy violators | Admin | I want to remove policy violators | 3 | Low | Final | Admin enforcement capability
46 | US 03.08.01 | 5: Admin Management | Review notification logs | Admin | I want to review notification logs | 5 | Medium | Final | Audit and troubleshooting tool
185

## By Release
HALFWAY CHECKPOINT (MVP) - 27 Stories, 114 Points
ID | Epic | Title | Role | Story | Points | Risk | Release | Rationale | Dependencies
US 01.02.01 | 1: User Auth & Profile | Provide personal information (name, email, phone) | Entrant | I want to provide my personal information such as name, email and optional phone number in the app | 3 | Low | Halfway | Foundation for user profiles, simple form validation, low risk | None
US 01.02.02 | 1: User Auth & Profile | Update profile information | Entrant | I want to update information such as name, email and contact information on my profile | 2 | Low | Halfway | Basic CRUD operation, similar to create profile | US 01.02.01
US 01.07.01 | 1: User Auth & Profile | Device-based authentication (no password) | Entrant | I want device identification without password | 5 | High | Halfway | Custom approach, security critical, cryptographic device ID needed | US 01.02.01
US 01.01.03 | 2: Event Browsing | Browse events | Entrant | I want to be able to see a list of events that I can join the waiting list for | 3 | Low | Halfway | Core MVP feature, simple list display from Firestore | US 02.01.01
US 01.06.01 | 2: Event Browsing | View event details via QR code | Entrant | I want to view event details via QR code | 8 | High | Halfway | Camera integration, platform-specific, QR library needed | US 02.01.01
US 01.06.02 | 2: Event Browsing | Sign up for event by QR code | Entrant | I want to be able to sign up for an event by scanning QR code | 5 | Medium | Halfway | Combines QR scanning with join waiting list | US 01.06.01, US 01.01.01
US 01.01.02 | 2: Event Browsing | Leave waiting list | Entrant | I want to leave the waiting list for a specific event | 3 | Low | Halfway | Simple delete operation from waiting list | US 01.01.01
US 01.01.01 | 2: Event Browsing | Join waiting list for event | Entrant | I want to join the waiting list for a specific event | 5 | Medium | Halfway | Core MVP feature, must handle real-time updates, prevent duplicates | US 01.02.01, US 02.01.01
US 01.05.04 | 2: Event Browsing | See total entrants on waiting list | Entrant | I want to know how many total entrants are on the waiting list for an event | 2 | Low | Halfway | Simple count aggregation, useful for user to know odds | US 01.01.03
US 01.05.02 | 2: Event Browsing | Accept invitation to participate | Entrant | I want to be able to accept the invitation to register/sign up when chosen to participate in an event | 5 | Medium | Halfway | Core acceptance flow, state management, notifications | US 02.05.02
US 01.05.03 | 2: Event Browsing | Decline invitation to participate | Entrant | I want to be able to decline an invitation when chosen to participate in an event | 3 | Low | Halfway | Simple state change, triggers replacement draw | US 02.05.02
US 01.05.01 | 2: Event Browsing | Another chance if selected user declines | Entrant | I want another chance to be chosen from the waiting list if a selected user declines | 5 | Medium | Halfway | Core lottery feature, replacement draws, depends on lottery and notification systems | US 01.01.01, US 02.05.02
US 01.04.01 | 3: Notifications | Notification when chosen (won lottery) | Entrant | I want to receive notification when I am chosen to participate from the waiting list | 5 | Medium | Halfway | Core MVP feature, requires notification service integration | US 02.05.02
US 01.04.02 | 3: Notifications | Notification when not chosen (lost lottery) | Entrant | I want to receive notification when I am not chosen on the app | 3 | Low | Halfway | Similar to selection but simpler content | US 02.05.02
US 02.07.01 | 3: Notifications | Send notifications to waiting list | Organizer | I want to send notifications to all entrants on the waiting list | 5 | Medium | Halfway | Organizer communication tool, bulk notification delivery | US 01.01.01
US 02.07.02 | 3: Notifications | Send notifications to selected entrants | Organizer | I want to send notifications to all selected entrants | 3 | Low | Halfway | Same as above but for selected only, narrower recipient pool | US 02.05.02
US 02.01.01 | 4: Event Management | Create event with QR code | Organizer | I want to create a new event and generate a unique promotional QR code | 8 | High | Halfway | Multiple complex components, QR generation, image handling, 8 pts justified | US 01.02.01
US 02.01.04 | 4: Event Management | Set registration period | Organizer | I want to set registration period | 3 | Low | Halfway | Part of event creation form, simple validation logic | US 02.01.01
US 02.02.01 | 4: Event Management | View waiting list | Organizer | I want to view the list of entrants who joined my event waiting list | 5 | Medium | Halfway | Important monitoring tool, fetch and display real-time data | US 01.01.01, US 02.01.01
US 02.04.01 | 4: Event Management | Upload event poster | Organizer | I want to upload an event poster to the event details page | 5 | Medium | Halfway | Visual appeal, image upload handling, Firebase Storage integration | US 02.01.01
US 02.04.02 | 4: Event Management | Update event poster | Organizer | I want to update an event poster | 3 | Low | Halfway | Extension of upload, simple replace operation | US 02.04.01
US 02.05.01 | 4: Event Management | Organizer triggers lottery draw | Organizer | I want to draw lottery (organizer initiates draw after registration closes) | 3 | Medium | Halfway | UI trigger for lottery system, workflow integration | US 02.05.02
US 02.05.02 | 4: Event Management | Lottery algorithm (random sampling) | System | I want to set the system to sample a specified number of attendees | 8 | High | Halfway | Core system integrity, fairness critical, rigorous testing needed | US 01.01.01
US 02.05.03 | 4: Event Management | Draw replacement applicant | Organizer | I want to draw a replacement applicant when selected applicant cancels | 5 | Medium | Halfway | Core feature for managing declines, uses lottery algorithm | US 02.05.02, US 01.04.01
US 02.06.01 | 4: Event Management | View selected/invited entrants | Organizer | I want to view a list of all chosen entrants who are invited to apply | 3 | Low | Halfway | Important status monitoring, similar to waiting list view | US 02.05.02
US 02.06.03 | 4: Event Management | View final enrolled list | Organizer | I want to see a final list of entrants who enrolled for the event | 3 | Low | Halfway | Essential for attendance tracking | US 01.05.02
US 02.06.04 | 4: Event Management | Cancel entrant (organizer action) | Organizer | I want to cancel entrants that did not sign up for the event | 3 | Low | Halfway | Management/enforcement tool, simple status change | US 02.06.03
FINAL RELEASE - 19 Stories, 71 Points
ID | Epic | Title | Role | Story | Points | Risk | Release | Rationale | Dependencies
US 01.04.03 | 1: User Auth & Profile | Opt out of notifications | Entrant | I want to opt out of notifications | 3 | Low | Final | Simple toggle setting in preferences | US 01.02.01
US 01.02.04 | 1: User Auth & Profile | Delete profile | Entrant | I want to delete my profile if I no longer wish to use the app | 3 | Low | Final | Data deletion important (GDPR), cascade deletes needed | US 01.02.01
US 01.01.04 | 2: Event Browsing | Filter events by interest and availability | Entrant | I want to filter events by interest and availability | 8 | High | Final | Complex search logic, database indexing needed, performance critical | US 01.01.03
US 01.05.05 | 2: Event Browsing | Understand lottery selection criteria | Entrant | I want to be informed about the criteria or guidelines for the lottery selection process | 2 | Low | Final | Educational/transparency feature, simple informational content | US 02.05.02
US 01.02.03 | 2: Event Browsing | View event registration history | Entrant | I want to have a history of events I have registered for, whether I was selected or not | 5 | Medium | Final | Nice-to-have feature for user, requires data aggregation | US 01.01.01
US 02.07.03 | 3: Notifications | Send notifications to cancelled entrants | Organizer | I want to send a notification to all cancelled entrants | 2 | Low | Final | Optional communication, very limited recipient pool | US 02.05.03
US 02.02.02 | 4: Event Management | View map of entrants | Organizer | I want to see on a map where entrants joined my event waiting list from | 8 | High | Final | Google Maps API integration, privacy concerns, not MVP | US 01.02.01, US 02.02.03
US 02.02.03 | 4: Event Management | Enable/disable geolocation | Organizer | I want to enable or disable the geolocation requirement for my event | 5 | Medium | Final | Companion to map feature, privacy control | US 02.01.01
US 02.03.01 | 4: Event Management | Limit waiting list size (optional) | Organizer | I want to OPTIONALLY limit the number of entrants who can join my waiting list | 3 | Low | Final | Optional feature for organizer control | US 02.01.01
US 02.06.02 | 4: Event Management | View cancelled entrants | Organizer | I want to see a list of all the cancelled entrants | 3 | Low | Final | Tracking feature for management
US 02.06.05 | 4: Event Management | Export enrolled list (CSV) | Organizer | I want to export a final list of entrants in CSV format | 5 | Medium | Final | Data export for external use, CSV generation | US 02.06.03
US 03.01.01 | 5: Admin Management | Remove events | Admin | I want to remove events | 3 | Low | Final | Admin moderation capability
US 03.02.01 | 5: Admin Management | Remove profiles | Admin | I want to remove profiles | 3 | Low | Final | Admin moderation capability
US 03.03.01 | 5: Admin Management | Remove images | Admin | I want to remove images | 2 | Low | Final | Admin moderation capability
US 03.04.01 | 5: Admin Management | Browse events (admin view) | Admin | I want to browse events | 3 | Low | Final | Admin visibility into system
US 03.05.01 | 5: Admin Management | Browse profiles (admin view) | Admin | I want to browse profiles | 3 | Low | Final | Admin visibility into system
US 03.06.01 | 5: Admin Management | Browse images (admin view) | Admin | I want to be able to browse images that are uploaded | 2 | Low | Final | Admin visibility and moderation
US 03.07.01 | 5: Admin Management | Remove policy violators | Admin | I want to remove policy violators | 3 | Low | Final | Admin enforcement capability
US 03.08.01 | 5: Admin Management | Review notification logs | Admin | I want to review notification logs | 5 | Medium | Final | Audit and troubleshooting tool

## By Risk
HIGH RISK (6 Stories, 45 Points)
ID | Epic | Title | Role | Story | Points | Risk | Release | Rationale | Dependencies
US 01.07.01 | 1: User Auth & Profile | Device-based authentication (no password) | Entrant | I want device identification without password | 5 | High | Halfway | Custom approach, security critical, cryptographic device ID needed | US 01.02.01
US 01.01.04 | 2: Event Browsing | Filter events by interest and availability | Entrant | I want to filter events by interest and availability | 8 | High | Final | Complex search logic, database indexing needed, performance critical | US 01.01.03
US 01.06.01 | 2: Event Browsing | View event details via QR code | Entrant | I want to view event details via QR code | 8 | High | Halfway | Camera integration, platform-specific, QR library needed | US 02.01.01
US 02.01.01 | 4: Event Management | Create event with QR code | Organizer | I want to create a new event and generate a unique promotional QR code | 8 | High | Halfway | Multiple complex components, QR generation, image handling, 8 pts justified | US 01.02.01
US 02.02.02 | 4: Event Management | View map of entrants | Organizer | I want to see on a map where entrants joined my event waiting list from | 8 | High | Final | Google Maps API integration, privacy concerns, not MVP | US 01.02.01, US 02.02.03
US 02.05.02 | 4: Event Management | Lottery algorithm (random sampling) | System | I want to set the system to sample a specified number of attendees | 8 | High | Halfway | Core system integrity, fairness critical, rigorous testing needed | US 01.01.01
MEDIUM RISK (14 Stories, 68 Points)
ID | Epic | Title | Role | Story | Points | Risk | Release | Rationale | Dependencies
US 01.06.02 | 2: Event Browsing | Sign up for event by QR code | Entrant | I want to be able to sign up for an event by scanning QR code | 5 | Medium | Halfway | Combines QR scanning with join waiting list | US 01.06.01, US 01.01.01
US 01.01.01 | 2: Event Browsing | Join waiting list for event | Entrant | I want to join the waiting list for a specific event | 5 | Medium | Halfway | Core MVP feature, must handle real-time updates, prevent duplicates | US 01.02.01, US 02.01.01
US 01.05.02 | 2: Event Browsing | Accept invitation to participate | Entrant | I want to be able to accept the invitation to register/sign up when chosen to participate in an event | 5 | Medium | Halfway | Core acceptance flow, state management, notifications | US 02.05.02
US 01.05.01 | 2: Event Browsing | Another chance if selected user declines | Entrant | I want another chance to be chosen from the waiting list if a selected user declines | 5 | Medium | Halfway | Core lottery feature, replacement draws, depends on lottery and notification systems | US 01.01.01, US 02.05.02
US 01.02.03 | 2: Event Browsing | View event registration history | Entrant | I want to have a history of events I have registered for, whether I was selected or not | 5 | Medium | Final | Nice-to-have feature for user, requires data aggregation | US 01.01.01
US 01.04.01 | 3: Notifications | Notification when chosen (won lottery) | Entrant | I want to receive notification when I am chosen to participate from the waiting list | 5 | Medium | Halfway | Core MVP feature, requires notification service integration | US 02.05.02
US 02.07.01 | 3: Notifications | Send notifications to waiting list | Organizer | I want to send notifications to all entrants on the waiting list | 5 | Medium | Halfway | Organizer communication tool, bulk notification delivery | US 01.01.01
US 02.02.01 | 4: Event Management | View waiting list | Organizer | I want to view the list of entrants who joined my event waiting list | 5 | Medium | Halfway | Important monitoring tool, fetch and display real-time data | US 01.01.01, US 02.01.01
US 02.02.03 | 4: Event Management | Enable/disable geolocation | Organizer | I want to enable or disable the geolocation requirement for my event | 5 | Medium | Final | Companion to map feature, privacy control | US 02.01.01
US 02.04.01 | 4: Event Management | Upload event poster | Organizer | I want to upload an event poster to the event details page | 5 | Medium | Halfway | Visual appeal, image upload handling, Firebase Storage integration | US 02.01.01
US 02.05.01 | 4: Event Management | Organizer triggers lottery draw | Organizer | I want to draw lottery (organizer initiates draw after registration closes) | 3 | Medium | Halfway | UI trigger for lottery system, workflow integration | US 02.05.02
US 02.05.03 | 4: Event Management | Draw replacement applicant | Organizer | I want to draw a replacement applicant when selected applicant cancels | 5 | Medium | Halfway | Core feature for managing declines, uses lottery algorithm | US 02.05.02, US 01.04.01
US 02.06.05 | 4: Event Management | Export enrolled list (CSV) | Organizer | I want to export a final list of entrants in CSV format | 5 | Medium | Final | Data export for external use, CSV generation | US 02.06.03
US 03.08.01 | 5: Admin Management | Review notification logs | Admin | I want to review notification logs | 5 | Medium | Final | Audit and troubleshooting tool
LOW RISK (26 Stories, 72 Points)
ID | Epic | Title | Role | Story | Points | Risk | Release | Rationale | Dependencies
US 01.02.01 | 1: User Auth & Profile | Provide personal information (name, email, phone) | Entrant | I want to provide my personal information such as name, email and optional phone number in the app | 3 | Low | Halfway | Foundation for user profiles, simple form validation, low risk | None
US 01.02.02 | 1: User Auth & Profile | Update profile information | Entrant | I want to update information such as name, email and contact information on my profile | 2 | Low | Halfway | Basic CRUD operation, similar to create profile | US 01.02.01
US 01.04.03 | 1: User Auth & Profile | Opt out of notifications | Entrant | I want to opt out of notifications | 3 | Low | Final | Simple toggle setting in preferences | US 01.02.01
US 01.02.04 | 1: User Auth & Profile | Delete profile | Entrant | I want to delete my profile if I no longer wish to use the app | 3 | Low | Final | Data deletion important (GDPR), cascade deletes needed | US 01.02.01
US 01.01.03 | 2: Event Browsing | Browse events | Entrant | I want to be able to see a list of events that I can join the waiting list for | 3 | Low | Halfway | Core MVP feature, simple list display from Firestore | US 02.01.01
US 01.01.02 | 2: Event Browsing | Leave waiting list | Entrant | I want to leave the waiting list for a specific event | 3 | Low | Halfway | Simple delete operation from waiting list | US 01.01.01
US 01.05.04 | 2: Event Browsing | See total entrants on waiting list | Entrant | I want to know how many total entrants are on the waiting list for an event | 2 | Low | Halfway | Simple count aggregation, useful for user to know odds | US 01.01.03
US 01.05.03 | 2: Event Browsing | Decline invitation to participate | Entrant | I want to be able to decline an invitation when chosen to participate in an event | 3 | Low | Halfway | Simple state change, triggers replacement draw | US 02.05.02
US 01.05.05 | 2: Event Browsing | Understand lottery selection criteria | Entrant | I want to be informed about the criteria or guidelines for the lottery selection process | 2 | Low | Final | Educational/transparency feature, simple informational content | US 02.05.02
US 01.04.02 | 3: Notifications | Notification when not chosen (lost lottery) | Entrant | I want to receive notification when I am not chosen on the app | 3 | Low | Halfway | Similar to selection but simpler content | US 02.05.02
US 02.07.02 | 3: Notifications | Send notifications to selected entrants | Organizer | I want to send notifications to all selected entrants | 3 | Low | Halfway | Same as above but for selected only, narrower recipient pool | US 02.05.02
US 02.07.03 | 3: Notifications | Send notifications to cancelled entrants | Organizer | I want to send a notification to all cancelled entrants | 2 | Low | Final | Optional communication, very limited recipient pool | US 02.05.03
US 02.01.04 | 4: Event Management | Set registration period | Organizer | I want to set registration period | 3 | Low | Halfway | Part of event creation form, simple validation logic | US 02.01.01
US 02.03.01 | 4: Event Management | Limit waiting list size (optional) | Organizer | I want to OPTIONALLY limit the number of entrants who can join my waiting list | 3 | Low | Final | Optional feature for organizer control | US 02.01.01
US 02.04.02 | 4: Event Management | Update event poster | Organizer | I want to update an event poster | 3 | Low | Halfway | Extension of upload, simple replace operation | US 02.04.01
US 02.06.01 | 4: Event Management | View selected/invited entrants | Organizer | I want to view a list of all chosen entrants who are invited to apply | 3 | Low | Halfway | Important status monitoring, similar to waiting list view | US 02.05.02
US 02.06.02 | 4: Event Management | View cancelled entrants | Organizer | I want to see a list of all the cancelled entrants | 3 | Low | Final | Tracking feature for management
US 02.06.03 | 4: Event Management | View final enrolled list | Organizer | I want to see a final list of entrants who enrolled for the event | 3 | Low | Halfway | Essential for attendance tracking | US 01.05.02
US 02.06.04 | 4: Event Management | Cancel entrant (organizer action) | Organizer | I want to cancel entrants that did not sign up for the event | 3 | Low | Halfway | Management/enforcement tool, simple status change | US 02.06.03
US 03.01.01 | 5: Admin Management | Remove events | Admin | I want to remove events | 3 | Low | Final | Admin moderation capability
US 03.02.01 | 5: Admin Management | Remove profiles | Admin | I want to remove profiles | 3 | Low | Final | Admin moderation capability
US 03.03.01 | 5: Admin Management | Remove images | Admin | I want to remove images | 2 | Low | Final | Admin moderation capability
US 03.04.01 | 5: Admin Management | Browse events (admin view) | Admin | I want to browse events | 3 | Low | Final | Admin visibility into system
US 03.05.01 | 5: Admin Management | Browse profiles (admin view) | Admin | I want to browse profiles | 3 | Low | Final | Admin visibility into system
US 03.06.01 | 5: Admin Management | Browse images (admin view) | Admin | I want to be able to browse images that are uploaded | 2 | Low | Final | Admin visibility and moderation
US 03.07.01 | 5: Admin Management | Remove policy violators | Admin | I want to remove policy violators | 3 | Low | Final | Admin enforcement capability

## By Epic
1: User Auth & Profile - 5 Stories, 16 Points
ID | Epic | Title | Role | Story | Points | Risk | Release | Rationale | Dependencies
US 01.02.01 | 1: User Auth & Profile | Provide personal information (name, email, phone) | Entrant | I want to provide my personal information such as name, email and optional phone number in the app | 3 | Low | Halfway | Foundation for user profiles, simple form validation, low risk | None
US 01.02.02 | 1: User Auth & Profile | Update profile information | Entrant | I want to update information such as name, email and contact information on my profile | 2 | Low | Halfway | Basic CRUD operation, similar to create profile | US 01.02.01
US 01.07.01 | 1: User Auth & Profile | Device-based authentication (no password) | Entrant | I want device identification without password | 5 | High | Halfway | Custom approach, security critical, cryptographic device ID needed | US 01.02.01
US 01.04.03 | 1: User Auth & Profile | Opt out of notifications | Entrant | I want to opt out of notifications | 3 | Low | Final | Simple toggle setting in preferences | US 01.02.01
US 01.02.04 | 1: User Auth & Profile | Delete profile | Entrant | I want to delete my profile if I no longer wish to use the app | 3 | Low | Final | Data deletion important (GDPR), cascade deletes needed | US 01.02.01
2: Event Browsing - 12 Stories, 54 Points
ID | Epic | Title | Role | Story | Points | Risk | Release | Rationale | Dependencies
US 01.01.03 | 2: Event Browsing | Browse events | Entrant | I want to be able to see a list of events that I can join the waiting list for | 3 | Low | Halfway | Core MVP feature, simple list display from Firestore | US 02.01.01
US 01.01.04 | 2: Event Browsing | Filter events by interest and availability | Entrant | I want to filter events by interest and availability | 8 | High | Final | Complex search logic, database indexing needed, performance critical | US 01.01.03
US 01.06.01 | 2: Event Browsing | View event details via QR code | Entrant | I want to view event details via QR code | 8 | High | Halfway | Camera integration, platform-specific, QR library needed | US 02.01.01
US 01.06.02 | 2: Event Browsing | Sign up for event by QR code | Entrant | I want to be able to sign up for an event by scanning QR code | 5 | Medium | Halfway | Combines QR scanning with join waiting list | US 01.06.01, US 01.01.01
US 01.01.02 | 2: Event Browsing | Leave waiting list | Entrant | I want to leave the waiting list for a specific event | 3 | Low | Halfway | Simple delete operation from waiting list | US 01.01.01
US 01.01.01 | 2: Event Browsing | Join waiting list for event | Entrant | I want to join the waiting list for a specific event | 5 | Medium | Halfway | Core MVP feature, must handle real-time updates, prevent duplicates | US 01.02.01, US 02.01.01
US 01.05.04 | 2: Event Browsing | See total entrants on waiting list | Entrant | I want to know how many total entrants are on the waiting list for an event | 2 | Low | Halfway | Simple count aggregation, useful for user to know odds | US 01.01.03
US 01.05.02 | 2: Event Browsing | Accept invitation to participate | Entrant | I want to be able to accept the invitation to register/sign up when chosen to participate in an event | 5 | Medium | Halfway | Core acceptance flow, state management, notifications | US 02.05.02
US 01.05.03 | 2: Event Browsing | Decline invitation to participate | Entrant | I want to be able to decline an invitation when chosen to participate in an event | 3 | Low | Halfway | Simple state change, triggers replacement draw | US 02.05.02
US 01.05.01 | 2: Event Browsing | Another chance if selected user declines | Entrant | I want another chance to be chosen from the waiting list if a selected user declines | 5 | Medium | Halfway | Core lottery feature, replacement draws, depends on lottery and notification systems | US 01.01.01, US 02.05.02
US 01.05.05 | 2: Event Browsing | Understand lottery selection criteria | Entrant | I want to be informed about the criteria or guidelines for the lottery selection process | 2 | Low | Final | Educational/transparency feature, simple informational content | US 02.05.02
US 01.02.03 | 2: Event Browsing | View event registration history | Entrant | I want to have a history of events I have registered for, whether I was selected or not | 5 | Medium | Final | Nice-to-have feature for user, requires data aggregation | US 01.01.01
3: Notifications - 5 Stories, 18 Points
ID | Epic | Title | Role | Story | Points | Risk | Release | Rationale | Dependencies
US 01.04.01 | 3: Notifications | Notification when chosen (won lottery) | Entrant | I want to receive notification when I am chosen to participate from the waiting list | 5 | Medium | Halfway | Core MVP feature, requires notification service integration | US 02.05.02
US 01.04.02 | 3: Notifications | Notification when not chosen (lost lottery) | Entrant | I want to receive notification when I am not chosen on the app | 3 | Low | Halfway | Similar to selection but simpler content | US 02.05.02
US 02.07.01 | 3: Notifications | Send notifications to waiting list | Organizer | I want to send notifications to all entrants on the waiting list | 5 | Medium | Halfway | Organizer communication tool, bulk notification delivery | US 01.01.01
US 02.07.02 | 3: Notifications | Send notifications to selected entrants | Organizer | I want to send notifications to all selected entrants | 3 | Low | Halfway | Same as above but for selected only, narrower recipient pool | US 02.05.02
US 02.07.03 | 3: Notifications | Send notifications to cancelled entrants | Organizer | I want to send a notification to all cancelled entrants | 2 | Low | Final | Optional communication, very limited recipient pool | US 02.05.03
4: Event Management - 16 Stories, 73 Points
ID | Epic | Title | Role | Story | Points | Risk | Release | Rationale | Dependencies
US 02.01.01 | 4: Event Management | Create event with QR code | Organizer | I want to create a new event and generate a unique promotional QR code | 8 | High | Halfway | Multiple complex components, QR generation, image handling, 8 pts justified | US 01.02.01
US 02.01.04 | 4: Event Management | Set registration period | Organizer | I want to set registration period | 3 | Low | Halfway | Part of event creation form, simple validation logic | US 02.01.01
US 02.02.01 | 4: Event Management | View waiting list | Organizer | I want to view the list of entrants who joined my event waiting list | 5 | Medium | Halfway | Important monitoring tool, fetch and display real-time data | US 01.01.01, US 02.01.01
US 02.02.02 | 4: Event Management | View map of entrants | Organizer | I want to see on a map where entrants joined my event waiting list from | 8 | High | Final | Google Maps API integration, privacy concerns, not MVP | US 01.02.01, US 02.02.03
US 02.02.03 | 4: Event Management | Enable/disable geolocation | Organizer | I want to enable or disable the geolocation requirement for my event | 5 | Medium | Final | Companion to map feature, privacy control | US 02.01.01
US 02.03.01 | 4: Event Management | Limit waiting list size (optional) | Organizer | I want to OPTIONALLY limit the number of entrants who can join my waiting list | 3 | Low | Final | Optional feature for organizer control | US 02.01.01
US 02.04.01 | 4: Event Management | Upload event poster | Organizer | I want to upload an event poster to the event details page | 5 | Medium | Halfway | Visual appeal, image upload handling, Firebase Storage integration | US 02.01.01
US 02.04.02 | 4: Event Management | Update event poster | Organizer | I want to update an event poster | 3 | Low | Halfway | Extension of upload, simple replace operation | US 02.04.01
US 02.05.01 | 4: Event Management | Organizer triggers lottery draw | Organizer | I want to draw lottery (organizer initiates draw after registration closes) | 3 | Medium | Halfway | UI trigger for lottery system, workflow integration | US 02.05.02
US 02.05.02 | 4: Event Management | Lottery algorithm (random sampling) | System | I want to set the system to sample a specified number of attendees | 8 | High | Halfway | Core system integrity, fairness critical, rigorous testing needed | US 01.01.01
US 02.05.03 | 4: Event Management | Draw replacement applicant | Organizer | I want to draw a replacement applicant when selected applicant cancels | 5 | Medium | Halfway | Core feature for managing declines, uses lottery algorithm | US 02.05.02, US 01.04.01
US 02.06.01 | 4: Event Management | View selected/invited entrants | Organizer | I want to view a list of all chosen entrants who are invited to apply | 3 | Low | Halfway | Important status monitoring, similar to waiting list view | US 02.05.02
US 02.06.02 | 4: Event Management | View cancelled entrants | Organizer | I want to see a list of all the cancelled entrants | 3 | Low | Final | Tracking feature for management
US 02.06.03 | 4: Event Management | View final enrolled list | Organizer | I want to see a final list of entrants who enrolled for the event | 3 | Low | Halfway | Essential for attendance tracking | US 01.05.02
US 02.06.04 | 4: Event Management | Cancel entrant (organizer action) | Organizer | I want to cancel entrants that did not sign up for the event | 3 | Low | Halfway | Management/enforcement tool, simple status change | US 02.06.03
US 02.06.05 | 4: Event Management | Export enrolled list (CSV) | Organizer | I want to export a final list of entrants in CSV format | 5 | Medium | Final | Data export for external use, CSV generation | US 02.06.03
5: Admin Management - 8 Stories, 24 Points
ID | Epic | Title | Role | Story | Points | Risk | Release | Rationale | Dependencies
US 03.01.01 | 5: Admin Management | Remove events | Admin | I want to remove events | 3 | Low | Final | Admin moderation capability
US 03.02.01 | 5: Admin Management | Remove profiles | Admin | I want to remove profiles | 3 | Low | Final | Admin moderation capability
US 03.03.01 | 5: Admin Management | Remove images | Admin | I want to remove images | 2 | Low | Final | Admin moderation capability
US 03.04.01 | 5: Admin Management | Browse events (admin view) | Admin | I want to browse events | 3 | Low | Final | Admin visibility into system
US 03.05.01 | 5: Admin Management | Browse profiles (admin view) | Admin | I want to browse profiles | 3 | Low | Final | Admin visibility into system
US 03.06.01 | 5: Admin Management | Browse images (admin view) | Admin | I want to be able to browse images that are uploaded | 2 | Low | Final | Admin visibility and moderation
US 03.07.01 | 5: Admin Management | Remove policy violators | Admin | I want to remove policy violators | 3 | Low | Final | Admin enforcement capability
US 03.08.01 | 5: Admin Management | Review notification logs | Admin | I want to review notification logs | 5 | Medium | Final | Audit and troubleshooting tool

## Sprint Planning
SPRINT BREAKDOWN - 6 Sprints to MVP
Sprint | Title | Stories | Points | Focus | Result
Sprint 1 | Foundation & Auth | 5-6 | 16-20 | Set up Android project | Result: Users can create and manage profiles
Set up Firebase (Firestore, Storage, Auth, FCM)
Device-based authentication (US 01.07.01)
Create user profile (US 01.02.01)
Update user profile (US 01.02.02)
Basic navigation structure
Sprint 2 | Events & Browsing | 5-6 | 20-25 | Organizers can create events (US 02.01.01) | Result: Organizers can create events, Entrants can browse
Generate QR codes for events (US 02.01.01)
Set registration periods (US 02.01.04)
Upload event posters (US 02.04.01)
Entrants can browse events (US 01.01.03)
View event details
Sprint 3 | Waiting Lists | 5-6 | 20-25 | Join waiting list (US 01.01.01) | Result: Full waiting list functionality working
Leave waiting list (US 01.01.02)
QR code scanning to join (US 01.06.01, 01.06.02)
View waiting list count (US 01.05.04)
Organizer views waiting list (US 02.02.01)
Optional: Geolocation when joining (US 02.02.03)
Sprint 4 | Lottery & Draw | 5-6 | 20-25 | Lottery drawing algorithm (US 02.05.02) HIGH RISK | Result: Core lottery system works!
Set number of attendees to select (US 02.05.02)
Draw lottery and select winners
View selected entrants (US 02.06.01)
Draw replacement when someone declines (US 02.05.03)
Handle lottery results
Sprint 5 | Invitations | 4-5 | 15-20 | Accept invitation (US 01.05.02) | Result: Full invitation workflow complete
Decline invitation (US 01.05.03)
Another chance if someone declines (US 01.05.01)
Receive win notification (US 01.04.01)
Receive loss notification (US 01.04.02)
Update event posters (US 02.04.02)
Sprint 6 | Polish & Test | 3-4 | 10-15 | Send notifications to waiting list (US 02.07.01) | Result: MVP ready to present!
Send notifications to selected (US 02.07.02)
Opt-out of notifications (US 01.04.03)
Bug fixes from testing
Performance optimization
Prepare demo for half-way checkpoint
HALFWAY CHECKPOINT | Ready after Sprint 4-5 | 27 Stories | 114 Points
Sprint 7-9 | Final Release | 19 Stories | 71 Points | Filter events (US 01.01.04) | Result: Complete, production-ready app
Event history (US 01.02.03)
Delete profile (US 01.02.04)
Map view of entrants (US 02.02.02) ⚠️ HIGH RISK
Limit waiting list (US 02.03.01)
Cancel entrants (US 02.06.04)
Export to CSV (US 02.06.05)
Send to cancelled (US 02.07.03)
All admin features (US 03.01.01 - 03.08.01)
_____ Remove events
_____Remove profiles
_____Remove images
_____ Browse content
_____Remove Notification Logs